## Sheet1
| Start date | Duration(days) | End date
Researching technologies to be used for development and developing first prototype.
Research Entity Framework & WCF Services. | 2013-10-20 | 6 | 2013-10-25
Research client side and WCF communication. | 2013-10-25 | 6 | 2013-10-30
Develop first prototype, create database and connect client to the web service. | 2013-10-31 | 9 | 2013-11-08
Research and learn about implementation of Google Maps API. | 2013-11-08 | 4 | 2013-11-11
Setup and test GitHub repository. | 2013-11-11 | 2 | 2013-11-12
Develop basic version of the application. Implement all of the must haves |  | 1
Convert the initial prototype into a basic version of the application. | 2013-11-12 | 6 | 2013-11-17
Finalise the database design. | 2013-11-17 | 3 | 2013-11-19
Implement features from the 'must haves' category. | 2013-11-19 | 14 | 2013-12-02
Provide basic Google Maps functionality. | 2013-12-03 | 6 | 2013-12-08
Presentation week
Perform the mid-term presentation. | 2013-12-09 | 5 | 2013-12-13
Expand the application's featureset and developing additional features from the should haves set
Finish development of the basic featureset. Starting development of the 'should haves'. Please refer to problem specification for more details. | 2013-12-14 | 79 | 2014-03-02
Begin to work on dissertation
Producing dissertation. | 2014-01-02 | 131 | 2014-05-12
Complete development of additional functionality and developing extras and could haves
Development of the 'could haves' features. Please refer to the problem specification for more details. | 2014-03-02 | 72 | 2014-05-12
Project submission
Submit the dissertation and the completed project. | 2014-05-12 | 1 | 2014-05-12
Final demonstration
Perform the final presentation. | 2014-05-15 | 1 | 2014-05-15